## Sheet1
ATTACHMENT A - CONSULTANT SCHEDULE
Board Review Month | Phase Name | Month(s) | Key Activities | Deliverables
| Preparation & Project Launch | November 2025 - February 2026 | Define purpose, scope, roles, and timeline; Form Strategic Planning Committee (SPC); Review completed needs assessment; Hire consultant (reaching out to candidates outside of library field) | Planning charter; Communication plan; SPC roster
| Needs Assessment Review & Strategic Framing | November 2025 - February 2026 | Summarize insights from assessment; Conduct strategic framing workshop; Validate findings (coming out at the other end -- figuring out how to engage communities) | Needs assessment summary; Strategic themes
2026-02-01 | Meeting with the Board Executive Committee | February 2026 | Introduce the project and provide status update about the initiative | Presentation
| Vision, Mission & Values | March | Facilitate workshops; Draft/refine mission, vision, and values | Draft Vision, Mission, Values Statement; Feedback Summary
April | Meeting with the Board Executive Committee | April | Set the stage for the Board retreat in June | Status update and develop agenda for the retreat
| Strategic Priorities & Goal Setting | May | Define strategic focus areas and SMART goals based on assessment insights | Strategic Priorities; SMART Goals Document
June | Full Board Retreat | June | Consultant presents update as well as to solicitate input from the Board | PPT
| Action Planning & Resource Alignment | July | Assign responsibilities; Identify resources and partnerships; Develop KPIs, OKRs | Action Plans; KPI Framework; Budget Alignment
| Drafting & Public Feedback | August-September | Draft strategic plan; Solicit feedback from stakeholders | Draft Strategic Plan; Public Feedback Summary
October | Finalization & Board Approval | October | Revise and finalize plan; Obtain Board approval | Final Strategic Plan; Board Resolution
| Launch & Implementation Kickoff | November - | Launch communications; Begin implementation; Set up tracking systems | Launch Materials; Year 1 Work Plan; Evaluation Dashboard